## Sheet2
Integrated Transport Schemes Programme 2023
Scheme Type | Scheme Name and Location | District | Scheme Description | Anticipated Delivery (Spring/Summer/Autumn/Winter) | Scheme Status
Targeted Local Safety Schemes | Holdiford Road bridges, Milford | SBC | A feasibility study and consultation have been completed to evaluate signing and/or signalisation options for the canal and river bridges on Holdiford Road, which have restricted width and intervisibility. The scheme currently recommended for delivery requires the installation of traffic signals at the bridges. | Summer/Autumn 2023 | Design
Targeted Local Safety Schemes | Eastern Avenue / Grange Lane junction improvement | LDC | A preferred option has been designed that includes the installation of traffic signals, incorporating a right lane filter. Pedestrian links to the existing crossing will be improved and a new crossing facility will be installed on the northern arm of Grange Lane. Cycle provision will also be incorporated into the design, as well as coordination with Structural Maintenance teams to mprove the carriageway surface | Summer 2023 | Tender
Targeted Local Safety Schemes | Loxley crossroads, Kingstone, Uttoxeter | ESBC | To improve safety, it is recommended that the two side roads are offset to give better sight of the junction on approach. | Spring 2024 | Design
Community Liaison Schemes | Mill Lane Great Haywood | SBC | Provide a safe footway between Great Haywood and the canal basin and farm shops, linking between existing footways, to improve road safety for vulnerable road users. The scheme includes footway provision on one-way signal operation under the rail bridge. | TBC | Design
Community Liaison Schemes | Parking scheme, Yoxall Road, Newborough | ESBC | Provide restrictions in the centre of the village to ease congestion at peak times. Review the existing build-out on Duffield Lane that has received road safety concerns. Provide a 40mph buffer zone and reduction to 50mph towards Mitre Crossroads. | Spring 2023 | Completed
Community Liaison Schemes | A518 Weston to Uttoxeter speed limit review | ESBC | Site 1: A518 at Amerton – deliver a reduced speed limit to 50mph with associated signage for Amerton Working Farm as recommended in the January 2021 feasibility report. Site 2: Deliver a right turn ghost island and slow signs at Castlewood and consider issues on the uphill approach to junction Investigate options to improve the A51/A518 junction western approach at Weston and potential speeding issues at the A518/B5013 junction. Site 1 and 2 have been delivered and Site 3 will be delivered in line with recommendations from the feasibility study. | Autumn 2023 | Tender
Community Liaison Schemes | Traffic calming Anslow | ESBC | Measures to control traffic speeds throughout the village including construction of chicanes, speed limit alterations, and the introduction of waiting restrictions | Summer 2023 | Tender
Community Liaison Schemes | Heath Way Cannock controlled pedestrian crossing | CCDC | Replace the existing uncontrolled pedestrian crossing and refuge island on Heath Way near Rochester Way with a signal-controlled crossing as recommended by a feasibility report completed in 2020. | Summer 2023 | Tender
Community Liaison Schemes | Leek Road junction with A53 Buxton Road realignment and improvement | SMDC | Revised junction layout to slow vehicle manoeuvres and VAS and general improvements to lining and signing. | Autumn 2023 | Design
Community Liaison Schemes | Uttoxeter Parking Review - Market Place, Uttoxeter | ESBC | To implement the outcomes of the feasibility report undertaken in 2018 which will include changes to on-street parking, changes to on-street timings and cycle parking provision and the consideration of future on-street electric vehicle charging points in line with the EV Strategy. | Spring 2024 | Design
Community Liaison Schemes | Uttoxeter Parking Review - Back Lane, Uttoxeter | ESBC | To implement the outcomes of the feasibility report undertaken in 2018 which will include enforcement and engineering solutions to deter through traffic whilst also considering this as a future bus gate that could be enforced by ANPR cameras. | Spring 2024 | Design
Community Liaison Schemes | Uttoxeter Parking Review - Stone Road/Smithfield Road Junction, Uttoxeter | ESBC | To implement road safety improvements agreed in feasibility report from 2018 that seeks to improve safety at junctions and amends historical traffic regulation orders. The scheme proposal is to improve the safety and visibility of the crossing and to install revised guardrails to help direct pedestrians to the crossing. The crossing currently requires two School Crossing Patrol officers to direct and control students at school time. | Spring 2024 | Design
Community Liaison Schemes | Violet Way, Burton upon Trent | ESBC | The scheme will replace the existing speed cushions with full width road humps as well as provide the required road surfacing and road markings. | Winter 2023 | Design
Community Liaison Schemes | Brocton Road, Stafford | SBC | The feasibility study recommends the implementation of a weight restriction along Brocton Road to Sawpit Lane as well as signage and road marking improvements on the bend outside Dora Rose Care Home. There is funding committed from DHP of £6k. | Spring 2024 | Design
Community Liaison Schemes | Stramshall Traffic Calming | ESBC | Installation of 2 full width road humps in place of exisitng speed cushions to improve spped reduction through the village. | Autumn 2023 | Design
Community Liaison Schemes | Codsall Road, Dam Mill Codsall | SSDC | A DHP funded feasibility study was undertaken in 2022 in relation to the long term history of loss of control incidents. This identified the requirement of a community safety scheme, which will improve road safety, reduce the number of road safety incidents and reduce road traffic speed. The scheme will comprise of enhancements around the bend and measures to encourage spped reduction on approach to the bend | Spring 2024 | Design
2023/24 Countywide Commitments | Divisional Highway Programme | County wide | The Divisional Highway Programme is a Local Member Initiative that helps to fund highway and transport schemes prioritised by County Councillors, such as pedestrian safety, safety and congestion issues at local junctions, school traffic, HGV routing, speeding through villages, parking issues and rat-running on inappropriate roads. | All year | Ongoing
Transport Strategy Schemes | B5017 Corridor Improvements, Burton | ESBC | Deliver traffic calming and pedestrian improvements on the B5017 between Wellington Road/Shobnall Road and Postern Road, taking into account local community concerns, safety concerns around Shobnall Primary School and access to the hospital. | Deferred to 2024 (due to Structural Maintenance scheme) | Design
Transport Strategy Schemes | Uttoxeter Transport Package | ESBC | Completion of two Traffic Regulation Orders that deliver parking restrictions at Park Street, enabling a local bus service to be reinstated, and at Oldfields Road to improve safety at a sharp bend in the road. | Autumn 2023 | Design
Transport Strategy Schemes | Rugeley Town rail station | CCC | An improved link between Platform 2 at Rugeley Town Railway station and Horsefair and the town centre is proposed. This includes upgrading and lighting existing path to a shared use cycleway/footway. | TBC | Design
Transport Strategy Schemes | A34 Stafford Road / Eccleshall Road junction, Stone | SBC | Provision of a new pedestrian crossing across the A34 at Walton Island in Stone | Spring 2024 | Design
Transport Strategy Schemes | Street lighting and sustainable transport on Castle St and Railway St, Stafford | SBC | Improvements to the walking and cycling network between Castlefields and Stafford rail station, including enhanced lighting of the rail bridge on Castle Street; contra-flow cycle routes connecting to the National Cycle Network, with complementary 20mph zone; a cycle link between Railway Street and the station forecourt and enhancements to the off-road connection between Martin Drive and Castle Street. | TBC | Tender
Transport Strategy Schemes | Trent and Mersey Canal Towpath improvement Fradley to Kings Bromley Marina | LDC | Canal towpath upgrade between Fradley Junction and A515 Kings Bromley Marina to encourage walking and cycling | Spring 2023 | Construction (ongoing)
Transport Strategy Schemes | Abnalls Lane (A51 Lichfield to Burntwood) | LDC | Closure of Abnalls Lane from A51 to St Matthews Road Burntwood providing a safe walking and cycle route parallel to A5190. Pedestrian / cycle crossing provision may be required on A51 to serve Abnalls Lane. Public consultation has been completed on scheme options. | TBC | Design
Transport Strategy Schemes | Gaol Square Gyratory Traffic Signal Renewal, Stafford | SBC | To update and replace the existing traffic signal furniture to support the opening of the Stafford Western Access Route and enable the delivery of upgraded crossing facilities being delivered as part of the Chell Road active travel scheme. | Spring 2024 | Design
Transport Strategy Schemes | Amington School Street Project, Tamworth | TBC | The scheme is in Amington and runs between the existing cycle network that connects directly to the High School, along Florendine Street where the local primary school is situated, across the busy Tamworth Road, and over the canal to the towpath and the wider residential areas beyond the canal. | Spring 2024 | Design
Transport Strategy Schemes | Active Travel Scheme Station Street, Burton | ESBC | Completion of a cycle route along Station Street and Borough Road, between Guild Street and the rail station. Construction is due to commence in February 2023. | Spring 2023 | Construction (ongoing)
Transport Strategy Schemes | Active Travel Scheme Chell Road, Stafford | SBC | Delivery of a step-level cycle track along Chell Road, Stafford. This will complement the the recently completed SWAR by providing a high quality cycling/walkign link to the north of Stafford town centre, linking to the train station, the A34 and new facilities provided as part of SWAR. | Autumn 2023 | Tender
Transport Strategy Schemes | Shobnall Road, Burton upon Trent National Cycle Network | EBC | Installation of cycling infrastructure along Shobnall Road Burton upon Trent to link National Cycle Network route 54 from the access to Shobnall Fields with Anglesey Street, including installation of National Cycle Network signage. | Spring 2024 | Design
Transport Strategy Schemes | Newcastle-under-Lyme Towns Fund | NBC | Pedestrian and cycle improvements on Cemetery Road at A525 Gallowstree Lane junction A527 Barracks Road / Hassell Street pedestrian and cycle improvements | Autumn 2023 Spring 2024 | Design
Transport Strategy Schemes | East Staffordshire/Burton upon Trent Towns Fund | EBC | Cycling and pedestrian improvements will be delivered along Borough Road between the rail station and the town hall; along connecting roads through residential areas, together with improved cycle provision on the A511. | Deferred to 2024 | Design
Transport Strategy Schemes | Cycle Parking | ESBC, SBC, TBC, CCC, NBC | Provision of high quality cycle parking at key locations in Burton, Stafford, Newcastle, Cannock and Tamworth to support the new segregated cycle routes being delivered as part of Active Travel Funds | Winter 2023 | Design
Transport Strategy Schemes | Newcastle Greenway | NBC | Silverdale green way runs 2.7miles and is a well-used traffic-free section of NCN 551. There are currently 16 barriers identified on Silverdale Greenway. Funding is being provided by Sustrans to redesign 12 of the barriers to improve them to be LTN 1/20 compliant and accessible to all legitimate users. A feasibility report has been produced by Sustrans to support this project. | Spring 2024 | Design
Transport Strategy Schemes | Traffic Signal Renewal -Wellington Street/Derby Street Gyratory | ESBC | To update and replace the existing traffic signal furniture. | TBC | Design
Transport Strategy Schemes | Balls Canal Bridge, Hopwas - – Weight Restriction signage review | TBC | Implementation of Structural weight limit and all associated signage to discourage HGVs from entering Hints Lane and provide alternative routes. | Summer 2023 | Tender
Levelling Up Fund | Mill Street, Cannock | CCDC | Drainage and footway improvement works to provide an enhanced walking environment | Autumn 2023 | Design