## Programme
Programme Name: |  |  |  |  | Structural Maintenance Schemes
Programme Reporting Period: |  |  |  |  | January 2026 - March 2027
* All programmes of work are correct at the time of issuing. Deliverables and timeframes may be subject to change.
Road No. | Area | Div | Unique Street Reference | Road Name | Location | Treatment Area (if applicable) |  | Description of works | Aniticipated Programme Delivery Date (Spring/Summer/Autumn/Winter) | Status Update ( Programmed/Completed)
[6 empty] | Start Point | Finish Point
B5369 | N | N1 | 27000663 | Dimsdale Parade West (Jnc B5370 Watlands View) | Dimsdale | Junction area and approaches | Junction area and approaches | Carriageway resurfacing | Between 5th January 2026 and 27th February 2026 | Completed | 9
A0520 | N | N2 | 37701012 | Leek Road (Cellarhead Junction) | Cellarhead | Junction and approaches to Paton Drive | Junction and approaches to Paton Drive | Carriageway resurfacing | Between 2nd February 2026 and 6th November 2026 | Ongoing | 13
C0267 | N | W1(N) | 37601349 | Worston Lane | Shallowford | Worston Mill access area |  | Carriageway resurfacing | Between 5th January 2026 and 16th January 2026 | Completed
D2237 | N | N1 | 27001592 | Parkwood Drive/ Eastwood Rise | Madeley Park | Manor Road | Walls Wood | Carriageway resurfacing | Between 12th January 2026 and 27th March 2026 | Ongoing
D2190 | N | W1(N) | 37601591 | Kempsage Lane | Garmelow | Well Lane | Limit of adoption approx 415m west | Carriageway resurfacing | Between 23rd February 2026 and 20th March 2026 | Programmed
D2144 | N | W1(N) | 37601937 | Lower Heamies Lane | Eccleshall | Ecclesall Road | End of the cul-de-sac | Carriageway resurfacing | Between 7th April 2026 and 20th April 2026 | Programmed
D2031 | N | N1 | 27001395 | Bower End Lane | Madeley | Moss House Farm | Limit of adoption | Carriageway resurfacing | Between 21st April 2026 to 8th May 2026 | Programmed
A0520 | N | W1(N) | 37601473 | Newcastle Street / Radford Street | Stone | B5027 Newcastle Road | The Avenue | Carriageway resurfacing | Between 13th July 2026 and 7th September 2026 | Programmed
D1283 | N | N2 | 37701456 | Conway Road | Kynpersley | A527 Tunstall Road | Park Lane | Carriageway resurfacing | Between 9th November 2026 and 16th April 2027 | Programmed
A0527 | N | N2 | 37702152 | Meadows Way | Biddulph | Roundabout & approaches | Roundabout & approaches | Carriageway resurfacing | Between 20th April 2026 and 1st May 2026 | Programmed
A0518 | N | E1(N) | 12901293 | Derby Road / Town Meadows Way | Uttoxeter | Dovefields roundabout | A522 Dove Bank roundabout | Carriageway resurfacing | Between 11th May 2026 and 8th June 2026 | Programmed
U2040 | N | N1 | 27000988 | Gloucester Road / Newchapel Road | Kidsgrove | Whitehall Road | Mount Road | Carriageway resurfacing | Between 14th August 2026 and 12th February 2027 | Programmed
A0521 | N | N2 | 37700348 | Delphouse Road | Cheadle | Junction Draycott Cross Road | Junction Draycott Cross Road | Carriageway resurfacing | Between 29th June 2026 and 10th July 2026 | Programmed
U2079 | N | N1 | 27001180 | North Street | Newcastle | A52 Brunswick Street | West Street | Carriageway resurfacing | Between 15th February 2027 and 26th February 2027 | Programmed
D1279 | N | N2 | 37701699 | Wharf Road | Biddulph | South View / Sainsburys roundabout | South View / Sainsburys roundabout | Carriageway resurfacing | Between 1st March 2027 and 12th March 2027 | Programmed
A5013 | N | W1(N) | 37601421 | Stafford Road/Wheelwright Drive | Eccleshall | Junction area and approaches | Junction area and approaches | Carriageway resurfacing | Between 15th March 2027 and 26th March 2027 | Programmed
A0519 | N | N1 | 37600931, 37600932 | Newcastle Road, (SI works only) | Coates Heath / Mill Meece | Nelson Crescent | Yew Tree Fm access Slindon | Site Investigation Works | Between 1st June 2026 and 10th July 2026 | Programmed
A5190 | S | W2 | 5500280 | Lichfield Road | Cannock | Near Girton Road | Easter Way Island | Carriageway haunch reconstruction | Between 12th January 2026 and 16thJanuary 2026 | Completed
D4406 | S | W3 | 36701684 | Latherford Lane | Latherford | Featherstone Lane | Orchard Lane | Carriageway resurfacing | Between 23rd February 2026 and 17th April 2026 | Ongoing
D4352 | S | W3 | 36701031 | Orchard Lane | Shareshill | Saredon Road | Property : Orchard Farm | Carriageway resurfacing | Between 9th February 2026 and 13th February 2026 | Completed
D4324 | S | W2 | 36700992 | Poplar Lane | Cannock | Hatherton Road | Property : High House | Carriageway resurfacing | Between 2nd March 2026 and 20th March 2026 | Ongoing
B4154 | S | W2 | 5500411 | Walsall Road | Norton Canes | Norton Green Lane | Betty's Lane | Carriageway resurfacing | Between 7th April 2026 and 1st May 2026 | Programmed | 8
U4001 | S | E1(S) | 12900523 | Worthington Way | Burton upon Trent | Station Road junction |  | Carriageway resurfacing | Between 5th May 2026 and 18th May 2026 | Programmed
A5121 | S | E1(S) | 12900093 | Derby Road (Phase 3) | Burton upon Trent | Pirelli Roundabout surf joint | Derby Turns Roundabout surf joint | Carriageway resurfacing | Between 11th May 2026 and 24th August 2026 | Programmed
U4012 | S | E1(S) | 12900057 | Bretby Lane (Inclusive of Island) | Burton upon Trent | Ashby Road | Empire Road | Carriageway resurfacing | Between 25th August 2026 and 20th October 2026 | Programmed
A0460 | S | W3 | 36702063 | Lodge Lane Island | Saredon | Island that serves Saredon Road |  | Carriageway resurfacing | Between 27th July 2026 and 10th August 2026 | Programmed
C0368 | S | W2 | 5500076 | Pye Green Road crossroad | Hednesford | Serves Belt Road | Serves Limepit Lane | Carriageway resurfacing | Between 10th August 2026 and 7th September 2026 | Programmed
U5041 | S | W2 | 5500227 | Wimblebury Road | Hednesford | Keys Park Road | John Street | Carriageway resurfacing | Between 2nd November 2026 and 13th November 2026 | Programmed
C0169 | S | W3 | 36700342 | High Street | Pattingham | Access road to shops | Clive Road | Carriageway resurfacing | Between 19th October 2026 and 30th October 2026 | Programmed
D4609 | S | W3 | 36700530 | The Parkway | Perton | Shackleton Drive | Melrose Drive | Carriageway resurfacing | Between 19th October 2026 and 30th October 2026 | Programmed