## Programme
Programme Name: |  |  |  |  | Preventative Treatments (Footway)
Programme Reporting Period: |  |  |  |  | April 2026 - March 2027
* All programmes of work are correct at the time of issuing. Deliverables and timeframes may be subject to change.
Road No. | Area | Div | Unique Street Reference | Road Name | Location | Treatment Area (if applicable) |  | Description of works | Aniticipated Programme Delivery Date (Spring/Summer/Autumn/Winter) | Status Update ( Programmed/Completed)
[6 empty] | Start Point | Finish Point
D3212 | E2 | South | 23401265 | Rugeley Road | Chase Terrace | Duke Road | High Street | Footway Preventative Treatment | Spring / Summer | Programmed
C0146 | E2 | South | 23400137 | Chorley Road | Burntwood | Rugeley Road | Ogley Hay Road | Footway Preventative Treatment | Spring / Summer | Programmed
D3546 | E2 | South | 23400696 | Squirrells Hollow | Burntwood | Chorley Road | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3580 | E2 | South | 23401347 | Heath Way | Burntwood | Ogley Hay Road | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3152 | E2 | South | 23400416 | Rake Hill | Burntwood | Ogley Hay Road | Property : No.73 | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400401 | Shelley Road | Burntwood | Birch Terrace | Wordsworth Road | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400658 | Tennyson Aenue | Burntwood | Shelley Road | Birch Terrace | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400569 | Wordsworth Road | Burntwood | Shelley Road | Birch Terrace | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400083 | Masefield Close | Burntwood | Wordsworth Road | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400403 | Slade Road | Burntwood | Parkhill Road | Ogley Hay Road | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400744 | Redwood Drive | Burntwood | Linden Avenue | Slade Road | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400342 | Columbian Crescent | Burntwood | Redwood Drive | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400189 | Oregon Gardens | Burntwood | Redwood Drive | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400851 | Lombardy Grove | Burntwood | Redwood Drive | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23401063 | Corsican Close | Burntwood | Redwood Drive | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400427 | Oaken Gardens | Burntwood | Redwood Drive | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400928 | Aspen Grove | Burntwood | Redwood Drive | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400085 | Linden Avenue | Burntwood | Redwood Drive | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400915 | Alden Hurst | Burntwood | Lebanon Grove | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23401015 | Californian Grove | Burntwood | Lebanon Grove | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400945 | Beechen Grove | Burntwood | Lebanon Grove | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23401035 | Coppice Close | Burntwood | Lebanon Grove | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400506 | Carlton Crescent | Burntwood | Rochester Avenue | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23401075 | Cumberland Crescent | Burntwood | Rochester Avenue | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400190 | Stamford Crscent | Burntwood | Rochester Avenue | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400320 | Lambert Drive | Burntwood | Rochester Avenue | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400457 | Lulworth Road | Burntwood | Rochester Avenue | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400533 | Dursley Road | Burntwood | Rochester Avenue | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400359 | Eastwood Avenue | Burntwood | Ashmead Road | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23401023 | Clinton Crescent | Burntwood | Morley Road | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400558 | Halston Road | Burntwood | Ashmead Road | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3211 | E2 | South | 23400775 | Ogley Hay Road | Burntwood | Slade Road | Morley Road | Footway Preventative Treatment | Spring / Summer | Programmed
D3298 | E2 | South | 23400446 | Ogley Vale | Burntwood | Ogley Hay Road | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D3571 | E2 | South | 23401765 | Morlings Drive | Burntwood | Ogley Hay Road | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D4118 | W3 | South | 36700666 | Giggetty Lane | Wombourne | Common Road | Planks Lane | Footway Preventative Treatment | Spring / Summer | Programmed
D4125 | W3 | South | 36700990 | Planks Lane | Wombourne | Giggetty Lane | St. Brides Close | Footway Preventative Treatment | Spring / Summer | Programmed
D1291 | N2 | North | 37701027 | Garden Street | Leek | West Street | Belle Vue | Footway Preventative Treatment | Spring / Summer | Programmed
D1291 | N2 | North | 37700217 | Belle Vue | Leek | Albert Street | A523 Mill Street | Footway Preventative Treatment | Spring / Summer | Programmed
D1291 | N2 | North | 37701470 | Nunn Street | Leek | Garden Street | Byrom Street | Footway Preventative Treatment | Spring / Summer | Programmed
D1291 | N2 | North | 37701473 | Gaunt Street | Leek | Nunn Street | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1291 | N2 | North | 37701231 | Byrom Street | Leek | Nunn Street | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1291 | N2 | North | 37700403 | Frith Street | Leek | Belle Vue Road | Alma Street | Footway Preventative Treatment | Spring / Summer | Programmed
D1291 | N2 | North | 37700476 | Hillswood Avenue | Leek | Alma Street | Hillcrest | Footway Preventative Treatment | Spring / Summer | Programmed
D1291 | N2 | North | 37702028 | Abbey Wood Close | Leek | Hillswood Avenue | number 14 Abbey Wood Close | Footway Preventative Treatment | Spring / Summer | Programmed
D1291 | N2 | North | 37700496 | Hillcrest | Leek | Hillswood Avenue | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1291 | N2 | North | 37701122 | Albert Street | Leek | West Street | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1291 | N2 | North | 37700700 | School Street | Leek | West Street | Albert Street | Footway Preventative Treatment | Spring / Summer | Programmed
Div Fway | N2 | North | 37704038 | Link Fway | Leek | Belle Vue Road | Mill Street | Footway Preventative Treatment | Spring / Summer | Programmed
D1289 | N2 | North | 37701690 | Moorhouse Street | Leek | A523 Ashbourne Road | Wood Street | Footway Preventative Treatment | Spring / Summer | Programmed
D1289 | N2 | North | 37700718 | Southbank Street | Leek | Moorhouse Street | A520 Compton | Footway Preventative Treatment | Spring / Summer | Programmed
D1289 | N2 | North | 37700867 | Wood Street | Leek | A523 Ashbourne Road | Moorhouse Street | Footway Preventative Treatment | Spring / Summer | Programmed
D1289 | N2 | North | 37701022 | Grosvenor Street | Leek | Moorhouse Street | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1289 | N2 | North | 37700966 | Moorfields | Leek | Moorhouse Street | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1289 | N2 | North | 37700751 | Talbot Street | Leek | Moorhouse Street | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1289 | N2 | North | 37700981 | Livingstone Street | Leek | Talbot Street | Leonard Street | Footway Preventative Treatment | Spring / Summer | Programmed
D1289 | N2 | North | 37701465 | Leonard Street | Leek | A53 Haywood Street | Southbank Street | Footway Preventative Treatment | Spring / Summer | Programmed
D1289 | N2 | North | 37700712 | Shoobridge Street | Leek | A53 Haywood Street | Southbank Street | Footway Preventative Treatment | Spring / Summer | Programmed
D1289 | N2 | North | 37700984 | London Street | Leek | A53 Haywood Street | Southbank Street | Footway Preventative Treatment | Spring / Summer | Programmed
D1289 | N2 | North | 37700370 | Duke Street | Leek | A520 Compton | London Street | Footway Preventative Treatment | Spring / Summer | Programmed
D1289 | N2 | North | 37700682 | Prospect Place | Leek | A520 Compton | Cornhill Street | Footway Preventative Treatment | Spring / Summer | Programmed
D1289 | N2 | North | 37701221 | Cornhill Street | Leek | Prospect Place | end | Footway Preventative Treatment | Spring / Summer | Programmed
Div Fway | N2 | North | 37704102 | Link Fway | Leek | Leonard Street | Talbot Street | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700958 | Novi Lane | Leek | A53 Buxton Road | Ball Haye Green | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700836 | Windsor Drive | Leek | Novi Lane | Haregate Road | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37701017 | Haregate Road | Leek | Windsor Drive | Ball Haye Green | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37701245 | Ball Haye Green | Leek | Novi Lane | Ball Haye Road | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37701686 | Ball Haye Road | Leek | Ball Haye Green | Fowlchurch Road | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700802 | Vicarage Road | Leek | Fowlchurch Road | Ball Haye Road | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700991 | Lancaster Avenue | Leek | Ball Haye Road | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700962 | Nelson Street | Leek | Ball Haye Green | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700971 | Milk Street | Leek | Ball Haye Green | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700948 | Prince Street | Leek | Ball Haye Green | A53 Buxton Road | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37701816 | Hayes Close | Leek | Prince Street | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37701762 | Pump Street | Leek | Ball Haye Green | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37701139 | Hall Avenue | Leek | Ball Haye Green | Milner Terrace | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700684 | Provost Place | Leek | Hall Avenue | Novi Lane | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700610 | Milner Terrace | Leek | Novi Lane | Carlton Terrace | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37701766 | Haig Road | Leek | Milner Terrace | Milner Terrace | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37701480 | Carlton Terrace | Leek | Prince Street | Abbotts Road | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37701481 | Beatty Road | Leek | Carlton Terrace | Carlton Terrace | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37701483 | Weston Street | Leek | A53 Buxton Road | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700827 | Victoria Street | Leek | Weston Street | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37701482 | Shaw Place | Leek | A53 Buxton Road | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700193 | Abbotts Road | Leek | A53 Buxton Road | Horsecroft Crescent | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700763 | The Crescent | Leek | Abbotts Road | Abbotts Road | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700846 | Westminster Road (Inc cul de sac) | Leek | Abbotts Road | Haregate Road | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37701051 | Furmston Place | Leek | Westminster Road | ends | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700176 | Argles Road | Leek | Westminster Road | Haregate Road and Abbotts Road | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700485 | Horsecroft Crescent | Leek | Abbotts Road | Haregate Road | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700942 | Ramshaw View | Leek | Horsecroft Crescent | Queens Drive | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37701358 | Queens Drive | Leek | Horsecroft Crescent | Haregate Road | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700656 | Princess Avenue | Leek | Queens Drive | Windsor Drive | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700654 | Prince Charles Avenue | Leek | Princess Avenue | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700777 | Thorncliffe View | Leek | Princess Avenue | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37701359 | Tittesworth Avenue | Leek | Haregate Road | Haregate Road | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700949 | Priory Avenue | Leek | Haregate Road | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700301 | Churnet View | Leek | Haregate Road | ends | Footway Preventative Treatment | Spring / Summer | Programmed
D1292 | N2 | North | 37700938 | Roche Avenue | Leek | Haregate Road | end | Footway Preventative Treatment | Spring / Summer | Programmed
Div Fway | N2 | North | 37704081 | Link Fway | Leek | Windsor Drive | Link Fway | Footway Preventative Treatment | Spring / Summer | Programmed