## Programme
Programme Name: |  |  |  |  | Preventative Treatments (Footway)
Programme Reporting Period: |  |  |  |  | April 2026 - March 2027
* All programmes of work are correct at the time of issuing. Deliverables and timeframes may be subject to change.
Road No. | Area | Div | Unique Street Reference | Road Name | Location | Treatment Area (if applicable) |  | Description of works | Aniticipated Programme Delivery Date (Spring/Summer/Autumn/Winter) | Status Update ( Programmed/Completed)
[6 empty] | Start Point | Finish Point
U5116 | S | W2 | 5500600 | Badgers Way | Heath Hayes | Hayes Way | Hayes Way | Footway Preventative Treatment | Spring / Summer | Programmed
U5116 | S | W2 | 5500486 | Harebell Clolse | Heath Hayes | Badgers Way | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
U5116 | S | W2 | 5501129 | Heathland Close | Heath Hayes | Harebell Clolse | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
U5116 | S | W2 | 5500793 | Foxhill Close | Heath Hayes | Badgers Way | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
U5116 | S | W2 | 5500431 | Squirell Close | Heath Hayes | Badgers Way | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
U5116 | S | W2 | 5500708 | Charterfield Drive | Heath Hayes | Badgers Way | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
U5116 | S | W2 | 5500525 | Woodford Way | Heath Hayes | Charterfield Drive | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
U5116 | S | W2 | 5501128 | Wheatlands Close | Heath Hayes | Woodfield Way | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
U5116 | S | W2 | 5500184 | Thistledown Drive | Heath Hayes | Meadow Way | Millers Vale | Footway Preventative Treatment | Spring / Summer | Programmed
U5116 | S | W2 | 5500969 | Millers Vale | Heath Hayes | Spindlewood Close | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
U5116 | S | W2 | 5500154 | Spindlewood Close | Heath Hayes | Millers Vale | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
U5116 | S | W2 | 5500515 | Birchfields Drive | Heath Hayes | Millers Vale | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
U5116 | S | W2 | 5500520 | Ansty Drive | Heath Hayes | Badgers Way | Badgers Way | Footway Preventative Treatment | Spring / Summer | Programmed
U5116 | S | W2 | 5501149 | Redbrook Close | Heath Hayes | Ansty Drive | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
U5116 | S | W2 | 5500315 | Fairfield Close | Heath Hayes | Ansty Drive | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
U5116 | S | W2 | 5500926 | Lawnswood Close | Heath Hayes | Fairfield Close | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
U5116 | S | W2 | 5501150 | Denbury Close | Heath Hayes | Ansty Drive | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
U5116 | S | W2 | 5501055 | Carlton Close | Heath Hayes | Ansty Drive | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
U5116 | S | W2 | 5500676 | Buckland Close | Heath Hayes | Ansty Drive | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
U5116 | S | W2 | 5501054 | Langtree Close | Heath Hayes | Ansty Drive | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
U5116 | S | W2 | 5500960 | Meadow Way | Heath Hayes | Heath Way | Heath Way | Footway Preventative Treatment | Spring / Summer | Programmed
U5116 | S | W2 | 5500814 | Green Meadows | Heath Hayes | Meadow Way | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
U5116 | S | W2 | 5500333 | Clover Meadows | Heath Hayes | Meadow Way | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
U5116 | S | W2 | 5500731 | Condor Grove | Heath Hayes | Meadow Way | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
U5116 | S | W2 | 5500885 | Kestrel Grove | Heath Hayes | Meadow Way | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
U5116 | S | W2 | 5500459 | Osprey Grove | Heath Hayes | Meadow Way | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
U5116 | S | W2 | 5501148 | Eagle Grove | Heath Hayes | Meadow Way | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
U5116 | S | W2 | 5500510 | Buckingham Place | Heath Hayes | Meadow Way | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
U5116 | S | W2 | 5500341 | Edgemoor Meadow | Heath Hayes | Meadow Way | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
U5116 | S | W2 | 5501125 | Hopton Meadow | Heath Hayes | Meadow Way | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
U5116 | S | W2 | 5500287 | Kensigton Place | Heath Hayes | Meadow Way | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D4548 | S | W3 | 36700411 | Mercia Drive | Perton | The Parkway | The Parkway | Footway Preventative Treatment | Spring / Summer | Programmed
D4548 | S | W3 | 36701317 | Egelwin Close | Perton | Mercia Drive | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D4548 | S | W3 | 36701042 | Offas Drive | Perton | Mercia Drive | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D4548 | S | W3 | 36701352 | Cornovian Close | Perton | Offas Drive | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D4548 | S | W3 | 36701180 | Idonia Road | Perton | Mercia Drive | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D4548 | S | W3 | 36700222 | Athelstan Grove | Perton | Mercia Drive | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D4548 | S | W3 | 36701259 | Guthrum Close | Perton | Athelstan Grove | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D4548 | S | W3 | 36700221 | Penda Grove | Perton | Mercia Drive | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D4548 | S | W3 | 36701134 | Levington Close | Perton | Penda Grove | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D4548 | S | W3 | 36701243 | Harald Close | Perton | Mercia Drive | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
C0161 | S | W3 | 36700388 | Saredon Road | Cheslyn Hay | Wolverhampton Road | Property: School Coach Park | Footway Preventative Treatment | Spring / Summer | Programmed
B4156 | S | W3 | 36700179 | Low Street | Cheslyn Hay | Wolverhampton Road | Station Street | Footway Preventative Treatment | Spring / Summer | Programmed
B4156 | S | W3 | 36700434 | High Street | Cheslyn Hay | Wolverhampton Road | Station Street | Footway Preventative Treatment | Spring / Summer | Programmed
B4156 | S | W3 | 36700376 | Station Street | Cheslyn Hay | Low Street | Station Road (Railway Bridge) | Footway Preventative Treatment | Spring / Summer | Programmed
B4156 | S | W3 | 36700025 | Station Road | Great Wyrley | Station Road (Railway Bridge) | Walsall Road | Footway Preventative Treatment | Spring / Summer | Programmed
D4429 | S | W3 | 36700025 | Station Road(Service Rd) | Great Wyrley | Property: Hse No.34 | Property: Hse No.46 | Footway Preventative Treatment | Spring / Summer | Programmed
D4429 | S | W3 | 36701344 | Darges Lane | Great Wyrley | Station Street | A34 Walsall Road | Footway Preventative Treatment | Spring / Summer | Programmed
C0049 | S | W3 | 36701165 | Landywood Lane | Cheslyn Hay | High Street | Upper Landywood Lane | Footway Preventative Treatment | Spring / Summer | Programmed
C0049 | S | W3 | 36701164 | Landywood Lane | Great Wyrley | Upper Landywood Lane | Streets Lane | Footway Preventative Treatment | Spring / Summer | Programmed
U2074 | N | N1 | 27000677 | Cambridge Drive | NUL/Clayton | Clayton Lane | end | Footway Preventative Treatment | Spring / Summer | Programmed
U2074 | N | N1 | 27000585 | Suffolk Close | NUL/Clayton | Cambridge Drive | end | Footway Preventative Treatment | Spring / Summer | Programmed
U2074 | N | N1 | 27000682 | Durham Grove | NUL/Clayton | Cambridge Drive | end | Footway Preventative Treatment | Spring / Summer | Programmed
U2074 | N | N1 | 27001277 | Monmouth Place | NUL/Clayton | Cambridge Drive | end | Footway Preventative Treatment | Spring / Summer | Programmed
U2074 | N | N1 | 27000907 | Dorset Place | NUL/Clayton | Cambridge Drive | end | Footway Preventative Treatment | Spring / Summer | Programmed
U2074 | N | N1 | 27000650 | Hertford Grove | NUL/Clayton | Cornwall Avenue | end | Footway Preventative Treatment | Spring / Summer | Programmed
U2074 | N | N1 | 27000664 | Denbigh Close | NUL/Clayton | Cornwall Avenue | end | Footway Preventative Treatment | Spring / Summer | Programmed
A52 | N | N2 | 37700178 | Ash Bank Road | Werrington | Bridle Path | Oak Mount Road (DO NOT treat footways that have been reconstructed around Washerwall Lane junction | Footway Preventative Treatment | Spring / Summer | Programmed
B5051 | N | N2 | 37700484/37701265 | High Lane/Leek Road | Brown Edge | East side approx 30m south of Woodside Ave. West side approx 50m south of Woodside Ave (Allotments access) | East side Greenfield Avenue. West side Sandy Lane | Footway Preventative Treatment | Spring / Summer | Programmed
C0354 | N | N2 | 37700613 | Newpool Road | Biddulph/Knypersley | A527 Tunstall Road | Tower Hill Road | Footway Preventative Treatment | Spring / Summer | Programmed
D1279 | N | N2 | 37700570 | Meadowside | Biddulph/Knypersley | Newpool Road | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D1280 | N | N2 | 37701187 | Lyneside Road | Biddulph/Knypersley | Newpool Road | Brown Lees Road | Footway Preventative Treatment | Spring / Summer | Programmed
D1280 | N | N2 | 37700520 | Lanchester Close | Biddulph/Knypersley | Lyneside Road | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D1280 | N | N2 | 37701334 | Lagonda Close | Biddulph/Knypersley | Lyneside Road | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D1280 | N | N2 | 37700521 | Lancia Close | Biddulph/Knypersley | Lyneside Road | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D1280 | N | N2 | 37700436 | Hambleton Place | Biddulph/Knypersley | Lyneside Road | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D1280 | N | N2 | 37701030 | Gilbern Drive | Biddulph/Knypersley | Lyneside Road | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D1280 | N | N2 | 37700611 | Minerva Close | Biddulph/Knypersley | Lyneside Road | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D1280 | N | N2 | 37700939 | Royce Avenue | Biddulph/Knypersley | Lyneside Road | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D1280 | N | N2 | 37700209 | Bateman Avenue | Biddulph/Knypersley | Lyneside Road | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D1280 | N | N2 | 37701768 | Farnham Drive | Biddulph/Knypersley | Lyneside Road | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D1280 | N | N2 | 37701180 | Healey Avenue | Biddulph/Knypersley | Lyneside Road | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D1280 | N | N2 | 37700546 | Lotus Avenue | Biddulph/Knypersley | Lyneside Road | Endon Drive | Footway Preventative Treatment | Spring / Summer | Programmed
D1280 | N | N2 | 37700819 | Turnlea Close | Biddulph/Knypersley | Lotus Avenue | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1280 | N | N2 | 37700506 | Kestrel Close | Biddulph/Knypersley | Lotus Avenue | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1280 | N | N2 | 37701335 | Knype Way | Biddulph/Knypersley | Lotus Avenue | Farnworth Close | Footway Preventative Treatment | Spring / Summer | Programmed
D1280 | N | N2 | 37700390 | Farnworth Close | Biddulph/Knypersley | Knype Way | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1280 | N | N2 | 37701061 | Endon Drive | Biddulph/Knypersley | Mansfield Drive | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1280 | N | N2 | 37700809 | Tower Close | Biddulph/Knypersley | Mansfield Drive | end | Footway Preventative Treatment | Spring / Summer | Programmed
C0354 | N | N2 | 37700787 | Tower Hill Road | Biddulph/Knypersley | Newpool Road | Newpool Terrace | Footway Preventative Treatment | Spring / Summer | Programmed
D1280 | N | N2 | 37700498 | James Way | Biddulph/Knypersley | Newpool Road | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1280 | N | N2 | 37701015 | Henley Avenue | Biddulph/Knypersley | Newpool Road | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1280 | N | N2 | 37700223 | Birch Avenue | Biddulph/Knypersley | Newpool Road | Henley Avenue | Footway Preventative Treatment | Spring / Summer | Programmed
D1280 | N | N2 | 37700739 | Stile Close | Biddulph/Knypersley | Tower Hill Road | end | Footway Preventative Treatment | Spring / Summer | Programmed
D1283 | N | N2 | 37700309 | Colwyn Drive | Knypersley | Orme Road | Mill Hayes Road | Footway Preventative Treatment | Spring / Summer | Programmed
D1283 | N | N2 | 37700602 | Nevin Avenue | Knypersley | Colwyn Drive | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D1283 | N | N2 | 37701023 | Gwyn Avenue | Knypersley | Colwyn Drive | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D1283 | N | N2 | 37700597 | Menai Drive | Knypersley | Colwyn Drive | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed
D1283 | N | N2 | 37700331 | Crossfield Avenue | Knypersley | A527 Tunstall Road | End of the cul-de-sac | Footway Preventative Treatment | Spring / Summer | Programmed